## Sheet1
Project Timeline |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
|  |  |  | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4 | W.1 | W.2 | W.3 | W.4
Project Kick-Off | bar: Month 1 W.1
Phase 1 | Gap Assessment | SC1, SC2 | 8W | bar: Month 1 W.1 to Month 2 W.4
Phase 2 | Business Impact Analysis | SC3 | 8W | bar: Month 3 W.1 to Month 4 W.4
| Risk Assessment | SC3 | 4W | bar: Month 5 W.1 to Month 5 W.4
Phase 3 | BC Strategies and Selection | SC2 | 5W | bar: Month 6 W.1 to Month 7 W.1
Phase 4 | Continuity Plan & Development | SC1 | 12W | bar: Month 5 W.1 to Month 7 W.4
Phase 6 | Training | SC3 | 8W | bar: Month 6 W.1 to Month 7 W.4
Awareness | bar: Month 6 W.1 to Month 6 W.4
Lead Implementer | bar: Month 7 W.1 to Month 7 W.2
Train The Trainer | bar: Month 7 W.3 to Month 7 W.4
Phase 5 | Business Continuity Testing | SC2 | 10W | bar: Month 7 W.3 to Month 9 W.4
Phase 7 | Review and Audit | SC1, SC2 | 8W | bar: Month 10 W.1 to Month 11 W.4
Project Closure | bar: Month 12 W.1 to Month 12 W.4
| total directorates | 10 directorates with each having average 7 units
| Group company | 13
| SC1 | 28
| SC2 | 31
| SC3 | 20
237
| every directorate | 2 days each
| every group co. | 3days
| BIA | 2 days each | 46
| risk | 2 days each | 46
| BC strategy | 3 days each | 70
| testing | 2 days each | 50
| training |  | 40 | Month 3 W.3: 354
| review |  | 40 | Month 3 W.3: 40
40
22

## Sheet2
SL. No. | Project Work Breakdown activities | Resource Type | Activity Type | Duration | Rate Card | Costing in AED
1 | Gap Assessment |  | Onsite |  |  | 0
2 | Business Impact Analysis |  | Onsite |  |  | 0
3 | Risk Assessment |  | Onsite |  |  | 0
4 | BC Strategies and Selection |  | Onsite |  |  | 0
5 | Continuity Plan & Development |  | Onsite |  |  | 0
6 | Training |  | Onsite |  |  | 0
| Awareness |  | Onsite | 30 |  | 0
| Lead Implementer |  | Onsite | 9 |  | 0
| Train The Trainer |  | Onsite | 10 |  | 0
7 | Business Continuity Testing |  | Onsite |  |  | 0
8 | Review and Audit |  | Onsite |  |  | 0
9 | Project Closure |  | Onsite |  |  | 0